## Esnad
AZ AL ZAYED TENTS & SHADES LLC |  |  | PROJECT MATERIAL PAYMENT RELEASE FORM
Department
Project Management
Purpose
Material Payment Release
BASIC INFORMATION
Project Name
Project Code
Client | [5 empty] | Requested Amount (AED) |  | 9827.95
Supplier |  | First Source
MATERIAL DETAILS
Description |  |  |  | Qty | Unit Price (AED) | Amount (AED) | Project Name
Columns- MS PIPE 168.3 mm-THK 5MM-6MTR |  |  |  | 6 | 440 | 2640 | Esnad
Arches- MS PIPE 73.1 mm-THK 3MM-6MTR |  |  |  | 26 | 125 | 3250 | Esnad
Truss Zigzag Pipe- MS PIPE 48.3mm-THK 2MM-6MTR |  |  |  | 13 | 48 | 624 | Esnad
Connector MS PIPE 60.3mm-THK 3MM-6MTR |  |  |  | 29 | 85 | 2465 | Esnad
TOTAL | [5 empty] | 8979
[5 empty] | TOTAL with VAT | 9427.95
Tranport | [5 empty] | 400
TOTAL AMOUNT | [5 empty] | 9827.95
PAYMENT RELEASE VERIFICATION (MOST IMPORTANT)
Current Project Progress |  |  | 10 | % | If this payment is released: |  |  |  | Expected Benefit
[5 empty] | 📅Materials will arrive on: 21-8-2026 |  |  |  | ☐ Production will continue
☐ Engineering |  |  | ☐ Painting |  | ⚙ Production can start on: after materials arrive |  |  |  | ☐ Project delay will be avoided
☐ Material Procurement |  |  | ☐ Fabric | [5 empty] | ☐ Client milestone will be achieved
☐ Fabrication |  |  | ☐ Dispatch | [5 empty] | ☐ Client payment can be claimed
☐ Installation |  |  |  |  | NEXT CLIENT PAYMENT
[5 empty] | Expected Invoice Value (AED) |  |  | Expected Collection Date
7 | REMARKS
Budget Available |  | ☐ Yes
Outstanding Supplier Balance |  |  | AED= 0
8 | APPROVAL FLOW
STEP | POSITION |  |  |  | NAME |  |  | SIGNATURE
1 | Requested By |  |  |  | Usman
2 | Approved By (Project Manager) |  |  |  | Hamza
3 | Verified By (Project Coordinator) |  |  |  | Zoha
4 | Accounts Verification |  |  |  | Zain
5 | Final Approval |  |  |  | Sadiya
6 | Payment Released By |  |  |  | Javeriya
9 | FINAL DECISION
● APPROVED FOR PAYMENT |  |  |  | Ⅱ HOLD PAYMENT |  |  |  | ✕ REJECTED
Reason (if Hold/Rejected):
⌁ QUALITY IN EVERY DETAIL |  |  |  | ◈ COMMITMENT IN EVERY PROJECT |  |  |  | 🤝 TRUST IN EVERY PAYMENT

## Naaji
AZ AL ZAYED TENTS & SHADES LLC |  |  | PROJECT MATERIAL PAYMENT RELEASE FORM
Department
Project Management
|  |  | ▣✓ Ensure Right Payment ¦ Ensure Right Progress ¦ Ensure Next Collection | [5 empty] | Purpose
Material Payment Release
BASIC INFORMATION
Payment Request No. |  | AZTS-0008 |  |  |  | Date |  | 2026-08-15
Project Name
Client | [5 empty] | Requested Amount (AED) |  | 2500
Supplier |  | Naaji |  |  |  | Currency |  | AED
MATERIAL DETAILS
Description |  |  |  | Qty | Unit Price (AED) | Amount (AED) | Project Name
Design calculation Arabico new LPO |  |  |  | 1 | 1000 | 1000 | Arabico
G zone new design calculation |  |  |  |  | 1500 | 1500 | G Zone
TOTAL with VAT
Tranport
TOTAL AMOUNT | [5 empty] | 2500
5 | PAYMENT RELEASE VERIFICATION (MOST IMPORTANT)
Current Project Progress |  |  | 5 | % | If this payment is released: |  |  |  | Expected Benefit
[5 empty] | 📅Materials will arrive on: |  |  |  | ☐ Production will continue
☐ Engineering |  |  | ☐ Painting |  | ⚙ Production can start on: n/a |  |  |  | ☐ Project delay will be avoided
☐ Material Procurement |  |  | ☐ Fabric |  | 🚚 Delivery date: |  |  |  | ☐ Client milestone will be achieved
☐ Fabrication |  |  | ☐ Dispatch |  | 👷 Installation date: |  |  |  | ☐ Client payment can be claimed
☐ Installation |  |  |  |  | NEXT CLIENT PAYMENT
[5 empty] | Expected Invoice Value (AED) |  |  | Expected Collection Date
7 | REMARKS
Budget Available |  | ☐ Yes
Outstanding Supplier Balance |  |  | AED= 0
8 | APPROVAL FLOW
STEP | POSITION |  |  |  | NAME |  |  | SIGNATURE
1 | Requested By |  |  |  | Usman
2 | Approved By (Project Manager) |  |  |  | Hamza
3 | Verified By (Project Coordinator) |  |  |  | Zoha
4 | Accounts Verification |  |  |  | Zain
5 | Final Approval |  |  |  | Sadiya
6 | Payment Released By |  |  |  | Javeriya
9 | FINAL DECISION
● APPROVED FOR PAYMENT |  |  |  | Ⅱ HOLD PAYMENT |  |  |  | ✕ REJECTED
Reason (if Hold/Rejected):
⌁ QUALITY IN EVERY DETAIL |  |  |  | ◈ COMMITMENT IN EVERY PROJECT |  |  |  | 🤝 TRUST IN EVERY PAYMENT

## Zahid
AZ AL ZAYED TENTS & SHADES LLC |  |  | PROJECT MATERIAL PAYMENT RELEASE FORM
Department
Project Management
|  |  | ▣✓ Ensure Right Payment ¦ Ensure Right Progress ¦ Ensure Next Collection | [5 empty] | Purpose
Material Payment Release
BASIC INFORMATION
Payment Request No. | [5 empty] | Date |  | 2026-08-15
Project Name |  | Arabico
Client | [5 empty] | Requested Amount (AED) |  | 320
Supplier | [5 empty] | Currency |  | AED
MATERIAL DETAILS
Description |  |  |  | Qty | Unit Price (AED) | Amount (AED) | Project Name
Black sand for Interlock |  |  |  | 1 | 320 | 320 | Arabico
TOTAL with VAT | [5 empty] | 320
Tranport | [5 empty] | 0
TOTAL AMOUNT | [5 empty] | 320
5 | PAYMENT RELEASE VERIFICATION (MOST IMPORTANT)
Current Project Progress |  |  | 5 | % | If this payment is released: |  |  |  | Expected Benefit
[5 empty] | 📅Materials will arrive on: |  |  |  | ☐ Production will continue
☐ Engineering |  |  | ☐ Painting |  | ⚙ Production can start on: n/a |  |  |  | ☐ Project delay will be avoided
☐ Material Procurement |  |  | ☐ Fabric |  | 🚚 Delivery date: |  |  |  | ☐ Client milestone will be achieved
☐ Fabrication |  |  | ☐ Dispatch |  | 👷 Installation date: |  |  |  | ☐ Client payment can be claimed
☐ Installation |  |  |  |  | NEXT CLIENT PAYMENT
[5 empty] | Expected Invoice Value (AED) |  |  | Expected Collection Date
[5 empty] | 70k |  |  | TBD
7 | REMARKS
Budget Available |  | ☐ Yes
Outstanding Supplier Balance |  |  | AED= 0
8 | APPROVAL FLOW
STEP | POSITION |  |  |  | NAME |  |  | SIGNATURE
1 | Requested By |  |  |  | Usman
2 | Approved By (Project Manager) |  |  |  | Hamza
3 | Verified By (Project Coordinator) |  |  |  | Zoha
4 | Accounts Verification |  |  |  | Zain
5 | Final Approval |  |  |  | Sadiya
6 | Payment Released By |  |  |  | Javeriya
9 | FINAL DECISION
● APPROVED FOR PAYMENT |  |  |  | Ⅱ HOLD PAYMENT |  |  |  | ✕ REJECTED
Reason (if Hold/Rejected):
⌁ QUALITY IN EVERY DETAIL |  |  |  | ◈ COMMITMENT IN EVERY PROJECT |  |  |  | 🤝 TRUST IN EVERY PAYMENT

## Dogma
AZ AL ZAYED TENTS & SHADES LLC |  |  | PROJECT MATERIAL PAYMENT RELEASE FORM
Department
Project Management
|  |  | ▣✓ Ensure Right Payment ¦ Ensure Right Progress ¦ Ensure Next Collection | [5 empty] | Purpose
Material Payment Release
BASIC INFORMATION
Payment Request No. |  | AZTS-0007 |  |  |  | proj value |  | 9975
Project Name |  | Al barsha + Inner Space
Project Code
Client |  | Al barsha + Inner Space |  |  |  | Requested Amount (AED) |  | 7551.025
Supplier |  | Marhaba |  |  |  | Currency |  | AED
MATERIAL DETAILS
Description |  |  |  | Qty | Unit Price (AED) | Amount (AED) | Project Name
ANCHOR BOLTS M20X400M length |  |  |  | 24 | 13 | 312 | dogma
MS RHS COLUMN 60X60-3MM-6MTR |  |  |  | 3 | 105 | 315 | dogma
MS RHS ARCH 60X60-3MM-6MTR |  |  |  | 4 | 105 | 420 | dogma
MS SHS TUBE Connector 50X50-3MM-6MTR |  |  |  | 6 | 90 | 540 | dogma
MS PLATE 1.2M X 2.4M-10MM |  |  |  | 1 | 810 | 810 | dogma
MS PLATE 1.2M X 2.4M-6MM |  |  |  | 1 | 450 | 450 | dogma
M16X120 NUT AND BOLTS |  |  |  | 30 | 1.5 | 45 | dogma
SELF TAPPING SCREW-BOX |  |  |  | 1 | 50 | 50 | dogma
M16X60 NUT AND BOLTS |  |  |  | 15 | 1.5 | 22.5 | dogma
PVC BLACKOUT 650 GSM 2.5X85MTR |  |  |  | 2 | 1438 | 2876 | dogma
PVC KEDDER |  |  |  | 100 | 5.5 | 550 | dogma
Single Channel |  |  |  | 6 | 30 | 180 | dogma
Double Channel |  |  |  | 4 | 60 | 240 | dogma
[5 empty] | TOTAL | 6810.5
TOTAL with VAT | [5 empty] | 7151.025
Tranport | [5 empty] | 400
TOTAL AMOUNT | [5 empty] | 7551.025
5 | PAYMENT RELEASE VERIFICATION (MOST IMPORTANT)
Current Project Progress |  |  | 90 | % | If this payment is released: |  |  |  | Expected Benefit
[5 empty] | 📅Materials will arrive on: 28-10-2026 |  |  |  | ☐ Production will continue
☐ Engineering |  |  | ☐ Painting |  | ⚙ Production can start on: n/a |  |  |  | ☐ Project delay will be avoided
☐ Material Procurement |  |  | ☐ Fabric |  | 🚚 Delivery date: Thursday 4rd |  |  |  | ☐ Client milestone will be achieved
☐ Fabrication |  |  | ☐ Dispatch |  | 👷 Installation date: next week |  |  |  | ☐ Client payment can be claimed
☐ Installation |  |  |  |  | NEXT CLIENT PAYMENT
[5 empty] | Expected Invoice Value (AED) |  |  | Expected Collection Date
[5 empty] | 3990 |  |  | TBD after purchase
7 | REMARKS
Budget Available |  | ☐ Yes
Outstanding Supplier Balance |  |  | AED= 0
8 | APPROVAL FLOW
STEP | POSITION |  |  |  | NAME |  |  | SIGNATURE
1 | Requested By |  |  |  | Usman
2 | Approved By (Project Manager) |  |  |  | Hamza
3 | Verified By (Project Coordinator) |  |  |  | Zoha
4 | Accounts Verification |  |  |  | Zain
5 | Final Approval |  |  |  | Sadiya
6 | Payment Released By |  |  |  | Javeriya
9 | FINAL DECISION
● APPROVED FOR PAYMENT |  |  |  | Ⅱ HOLD PAYMENT |  |  |  | ✕ REJECTED
Reason (if Hold/Rejected):
⌁ QUALITY IN EVERY DETAIL |  |  |  | ◈ COMMITMENT IN EVERY PROJECT |  |  |  | 🤝 TRUST IN EVERY PAYMENT

## Masri
AZ AL ZAYED TENTS & SHADES LLC |  |  | PROJECT MATERIAL PAYMENT RELEASE FORM
Department
Project Management
|  |  | ▣✓ Ensure Right Payment ¦ Ensure Right Progress ¦ Ensure Next Collection | [5 empty] | Purpose
Material Payment Release
BASIC INFORMATION
Project Name |  | Forca
Project value
Client | [5 empty] | Requested Amount (AED) |  | 44358.25
Supplier | [5 empty] | Currency |  | AED
MATERIAL DETAILS
Description |  |  |  | Qty | Unit Price (AED) | Amount (AED) | Supplier
MS PIPE 30 x60x 2mm-6 m |  |  |  | 52 | 55 | 2860 | First source
PVC BLACKOUT 850 GSM 2.5X50MTR |  |  |  | 13 | 1625 | 21125 | Marhaba
PVC BLACKOUT 650 GSM 2.5X50MTR |  |  |  | 8 | 1437.5 | 11500 | Marahaba
Kedder |  |  |  | 1160 | 5.5 | 6380 | Marahaba
[5 empty] | TOTAL | 41865
TOTAL with VAT | [5 empty] | 43958.25
Tranport | [5 empty] | 400
TOTAL AMOUNT | [5 empty] | 44358.25
5 | PAYMENT RELEASE VERIFICATION (MOST IMPORTANT)
Current Project Progress |  |  | 5 | % | If this payment is released: |  |  |  | Expected Benefit
[5 empty] | 📅Materials will arrive on: |  |  |  | ☐ Production will continue
☐ Engineering |  |  | ☐ Painting |  | ⚙ Production can start on: n/a |  |  |  | ☐ Project delay will be avoided
☐ Material Procurement |  |  | ☐ Fabric |  | 🚚 Delivery date: |  |  |  | ☐ Client milestone will be achieved
☐ Fabrication |  |  | ☐ Dispatch |  | 👷 Installation date: |  |  |  | ☐ Client payment can be claimed
☐ Installation |  |  |  |  | NEXT CLIENT PAYMENT
[5 empty] | Expected Invoice Value (AED) |  |  | Expected Collection Date
90000
7 | REMARKS
Budget Available |  | ☐ Yes
Outstanding Supplier Balance |  |  | AED= 0
8 | APPROVAL FLOW
STEP | POSITION |  |  |  | NAME |  |  | SIGNATURE
1 | Requested By |  |  |  | Usman
2 | Approved By (Project Manager) |  |  |  | Hamza
3 | Verified By (Project Coordinator) |  |  |  | Zoha
4 | Accounts Verification |  |  |  | Zain
5 | Final Approval |  |  |  | Sadiya
6 | Payment Released By |  |  |  | Javeriya
9 | FINAL DECISION
● APPROVED FOR PAYMENT |  |  |  | Ⅱ HOLD PAYMENT |  |  |  | ✕ REJECTED
Reason (if Hold/Rejected):
⌁ QUALITY IN EVERY DETAIL |  |  |  | ◈ COMMITMENT IN EVERY PROJECT |  |  |  | 🤝 TRUST IN EVERY PAYMENT

## Al daid
AZ AL ZAYED TENTS & SHADES LLC |  |  | PROJECT MATERIAL PAYMENT RELEASE FORM
Department
Project Management
|  |  | ▣✓ Ensure Right Payment ¦ Ensure Right Progress ¦ Ensure Next Collection | [5 empty] | Purpose
BASIC INFORMATION
Payment Request No. |  | AZTS-0006
Project Name |  | Inner space + forca
Project Code
Client |  | Inner space |  |  |  | Requested Amount (AED) |  | 8487.5
Supplier |  | First Source + Marhaba |  |  |  | Currency |  | AED
MATERIAL DETAILS
Description |  |  |  | Qty | Unit Price (AED) | Amount (AED) | Project Name
HDPE 340 GSM 3X40 |  |  |  | 5 | 1550 | 7750 | Marhaba
TOTAL | [5 empty] | 7750
[5 empty] | TOTAL with VAT | 8137.5
Tranport from locations | [5 empty] | 350
TOTAL AMOUNT | [5 empty] | 8487.5
PAYMENT RELEASE VERIFICATION (MOST IMPORTANT)
Current Project Progress |  |  | 10 | %
☐ Engineering |  |  | ☐ Painting |  | ⚙ Production can start on: after materials arrive
☐ Material Procurement |  |  | ☐ Fabric
☐ Fabrication |  |  | ☐ Dispatch
☐ Installation |  |  |  |  | NEXT CLIENT PAYMENT
[5 empty] | Expected Invoice Value (AED) |  |  | Expected Collection Date
[5 empty] | 72223 |  |  | TBD
7 | REMARKS
Budget Available |  | ☐ Yes
Outstanding Supplier Balance |  |  | AED= 0
8 | APPROVAL FLOW
STEP | POSITION |  |  |  | NAME |  |  | SIGNATURE
1 | Requested By |  |  |  | Usman
2 | Approved By (Project Manager) |  |  |  | Hamza
3 | Verified By (Project Coordinator) |  |  |  | Zoha
4 | Accounts Verification |  |  |  | Zain
5 | Final Approval |  |  |  | Sadiya
6 | Payment Released By |  |  |  | Javeriya
9 | FINAL DECISION
● APPROVED FOR PAYMENT |  |  |  | Ⅱ HOLD PAYMENT |  |  |  | ✕ REJECTED
Reason (if Hold/Rejected):
⌁ QUALITY IN EVERY DETAIL |  |  |  | ◈ COMMITMENT IN EVERY PROJECT |  |  |  | 🤝 TRUST IN EVERY PAYMENT

## arabico 2 steel
AZ AL ZAYED TENTS & SHADES LLC |  |  | PROJECT MATERIAL PAYMENT RELEASE FORM
Department
Project Management
|  |  | ▣✓ Ensure Right Payment ¦ Ensure Right Progress ¦ Ensure Next Collection | [5 empty] | Purpose
[10 empty] | Description | Qty | Unit Price (AED) | Amount (AED) | Project Name
[10 empty] | HDPE 340 GSM 3X50 | 4 | 1550 | 6200 | Arabico
BASIC INFORMATION | [9 empty] | MS PIPE INCH-THK 6inch 5MM-6MTR | 7 | 440 | 3080 | Arabico
Payment Request No. |  | AZTS-0006 | [7 empty] | D shackle | 160 | 8 | 1280 | Arabico
Project Name | [9 empty] | Webbing belt | 6 | 195 | 1170 | Arabico
Project Code | [9 empty] | 20x60 nuts and bolts | 81 | 7 | 567 | Arabico
Client |  | Arabico 2nd LPO |  |  |  | Requested Amount (AED) |  | 13525
Supplier |  | First Source + Marhaba |  |  |  | Currency |  | AED
MATERIAL DETAILS
Description |  |  |  | Qty | Unit Price (AED) | Amount (AED) | Project Name
Column MS PIPE 8INCH-THK 5MM-6MTR |  |  |  | 6 | 680 | 4080 | Arabico
Arches MS PIPE 4INCH-THK 4MM-6MTR |  |  |  | 6 | 210 | 1260 | Arabico
Connector MS PIPE 3INCH-THK 3MM-6MTR |  |  |  | 4 | 140 | 560 | Arabico
Tie rods MS PIPE 3INCH-THK 3MM-6MTR |  |  |  | 6 | 140 | 840 | Arabico
MS PLATE 1.2M X 2.4M-20MM |  |  |  | 1 | 1700 | 1700 | Arabico
MS PLATE 1.2M X 2.4M-6MM |  |  |  | 1 | 450 | 450 | Arabico
MS PLATE 1.2M X 2.4M-10MM |  |  |  | 2 | 810 | 1620 | Arabico
MS PLATE 1.2M X 2.4M-12MM |  |  |  | 2 | 995 | 1990 | Arabico
TOTAL | [5 empty] | 12500
[5 empty] | TOTAL with VAT | 13125
Tranport from locations | [5 empty] | 400
TOTAL AMOUNT | [5 empty] | 13525
PAYMENT RELEASE VERIFICATION (MOST IMPORTANT)
Current Project Progress |  |  | 10 | %
☐ Engineering |  |  | ☐ Painting |  | ⚙ Production can start on: after materials arrive
☐ Material Procurement |  |  | ☐ Fabric
☐ Fabrication |  |  | ☐ Dispatch
☐ Installation |  |  |  |  | NEXT CLIENT PAYMENT
[5 empty] | Expected Invoice Value (AED) |  |  | Expected Collection Date
[5 empty] | 72223 |  |  | TBD | [6 empty] | Description | Qty | Unit Price (AED) | Amount (AED) | Project Name
[15 empty] | Column MS PIPE 8INCH-THK 5MM-6MTR | 9 | 680 | 6120 | Arabico
7 | REMARKS | [13 empty] | Arches MS PIPE 4INCH-THK 4MM-6MTR | 9 | 210 | 1890 | Arabico
Budget Available |  | ☐ Yes | [12 empty] | Connector MS PIPE 3INCH-THK 3MM-6MTR | 6 | 140 | 840 | Arabico
Outstanding Supplier Balance |  |  | AED= 0 | [11 empty] | Tie rods MS PIPE 3INCH-THK 3MM-6MTR | 9 | 140 | 1260 | Arabico
[15 empty] | MS PLATE 1.2M X 2.4M-20MM | 1 | 1550 | 1550 | Arabico
[15 empty] | MS PLATE 1.2M X 2.4M-6MM | 1 | 390 | 390 | Arabico
[15 empty] | MS PLATE 1.2M X 2.4M-10MM | 2 | 680 | 1360 | Arabico
8 | APPROVAL FLOW | [13 empty] | MS PLATE 1.2M X 2.4M-12MM | 2 | 850 | 1700 | Arabico
STEP | POSITION |  |  |  | NAME |  |  | SIGNATURE
1 | Requested By |  |  |  | Usman | [10 empty] | Total |  | 15110
2 | Approved By (Project Manager) |  |  |  | Hamza | [10 empty] | with VAT |  | 15865.5
3 | Verified By (Project Coordinator) |  |  |  | Zoha
4 | Accounts Verification |  |  |  | Zain
5 | Final Approval |  |  |  | Sadiya
6 | Payment Released By |  |  |  | Javeriya
9 | FINAL DECISION
● APPROVED FOR PAYMENT |  |  |  | Ⅱ HOLD PAYMENT |  |  |  | ✕ REJECTED
Reason (if Hold/Rejected):
⌁ QUALITY IN EVERY DETAIL |  |  |  | ◈ COMMITMENT IN EVERY PROJECT |  |  |  | 🤝 TRUST IN EVERY PAYMENT

## Promser
AZ AL ZAYED TENTS & SHADES LLC |  |  | PROJECT MATERIAL PAYMENT RELEASE FORM
Department
Project Management
|  |  | ▣✓ Ensure Right Payment ¦ Ensure Right Progress ¦ Ensure Next Collection | [5 empty] | Purpose
Material Payment Release
BASIC INFORMATION
Payment Request No. |  | AZTS-0013 |  |  |  | Date |  | 2026-08-19
Project Name |  | Promser
Project Code
Supplier |  | First Source + Marhaba + Al bateen |  |  |  | Requested Amount (AED) |  | 13381
[6 empty] | Currency |  | AED
MATERIAL DETAILS
Description |  |  |  | Qty | Unit Price (AED) | Amount (AED) | Supplier
M20 THREAD ROD -2M |  |  |  | 16 | 55 | 880 | Al bateen
M20 nuts |  |  |  | 104 | 0.62 | 64.48 | Al bateen
M20 Washel |  |  |  | 104 | 0.25 | 26 | Al bateen
Hilti Chemical |  |  |  | 9 | 35 | 315 | Marhaba
PVC 900 GSM- 3x50 M Roll |  |  |  | 4 | 1875 | 7500 | Marhaba
MS PLATE 1.2M X 2.4M-30MM |  |  |  | 1 | 2775 | 2775 | first Source
MS PLATE 1.2M X 2.4M-16MM |  |  |  | 1 | 850 | 850 | first Source
Die |  |  |  | 3 | 25 | 75 | Marhaba
Paint, Epoxy thinner, Pu thinner |  |  |  | 1 | 535.5 | 535.5 | National paints
TOTAL | [5 empty] | 13020.98
[5 empty] | TOTAL with VAT | 13672.029
Tranport from 3 locations | [5 empty] | 500
TOTAL AMOUNT | [5 empty] | 14172.029
PAYMENT RELEASE VERIFICATION (MOST IMPORTANT)
Current Project Progress |  |  | 10 | % | If this payment is released: |  |  |  | Expected Benefit
[5 empty] | 📅Materials will arrive on: 12-8-2026 |  |  |  | ☐ Production will continue
☐ Engineering |  |  | ☐ Painting |  | ⚙ Production can start on: after materials arrive |  |  |  | ☐ Project delay will be avoided
☐ Material Procurement |  |  | ☐ Fabric | [5 empty] | ☐ Client milestone will be achieved
☐ Fabrication |  |  | ☐ Dispatch | [5 empty] | ☐ Client payment can be claimed
☐ Installation |  |  |  |  | NEXT CLIENT PAYMENT
[5 empty] | Expected Invoice Value (AED) |  |  | Expected Collection Date
[5 empty] | 1671 |  |  | 28/8/26
7 | REMARKS
Budget Available |  | ☐ Yes
Outstanding Supplier Balance |  |  | AED= 0
8 | APPROVAL FLOW
STEP | POSITION |  |  |  | NAME |  |  | SIGNATURE
1 | Requested By |  |  |  | Usman
2 | Approved By (Project Manager) |  |  |  | Hamza
3 | Verified By (Project Coordinator) |  |  |  | Zoha
4 | Accounts Verification |  |  |  | Zain
5 | Final Approval |  |  |  | Sadiya
6 | Payment Released By |  |  |  | Javeriya
9 | FINAL DECISION
● APPROVED FOR PAYMENT |  |  |  | Ⅱ HOLD PAYMENT |  |  |  | ✕ REJECTED
Reason (if Hold/Rejected):
⌁ QUALITY IN EVERY DETAIL |  |  |  | ◈ COMMITMENT IN EVERY PROJECT |  |  |  | 🤝 TRUST IN EVERY PAYMENT